Draft Minutes of Neighbourhood Plan Meeting

Monday, 2 December 2019

Present:,  	Helen Wallace (chair), Ian Jordan (Vice Chair), Catherine Harrison, Andrew Hill, Nigel Finch, Nick Miller (part of meeting)

Apologies:,	Stephen Lustig.

AGENDA ITEMS

- Minutes of 18 Nov meeting – agreed as accurate account of meeting.

- Update on Draft NP Document – more work has been done by AH & IJ on the draft.

Parish Council were updated on draft NP at last meeting and a date set to sign off draft version on 6 Jan 2020 following return from Babergh DC.

Discussed Traffic section and listed priorities to raise with Suffolk Highways at the walking the village meeting on 3 Dec.

ACTION – Please read latest draft version and send any comments to AH by Sun 8 Dec. Once comments incorporated AH to send draft to Babergh on 13/12.

- Action Plan Update – updated with regard to preparing draft plan and meetings organised.

Discussed preparation for Consultation Event;

- Possible date of Sat 18 January 2020, 11.00 – 13.00

- Send out personal invite letter to every household

- Discussed ideas for layout of display.

ACTION – HW to e Ian Poole re his ideas for 6 week consultation, to book display boards, and any useful proforma letters.

- Date of next meeting – Tuesday 17 December -5.30 Village Hall

Date for 2020 – Tuesday 7 January.