Draft Minutes of Neighbourhood Plan Meeting

Monday 20 January 2020

Present: 	Helen Wallace (chair), Andrew Hill. Nigel Finch, Catherine Harrison, Stephen Lustig, Nick Miller

Apologies:	Ian Poole (Consultant), Ian Jordan (Vice chair),

- Minutes of meeting 17 December 2019

The minutes of the meeting on 17 December were agreed and adopted with minor amendments.

Action: NM to contact IP regarding settlement gaps and whether we need a policy on this subject.

- Progress on Draft Neighbourhood Plan

Group referred to Ian P’s e mail indicating issues requiring further discussion tonight to progress the draft. (Ian P unable to attend tonight’s meeting due to family emergency). He will continue to work on draft plan this week following our input.

- Green spaces map needs to show the 12 plots identified. Action Nick M to amend map.

- Need to approach Babergh to inform that we would like to submit draft document soon and after approval of PC at meeting on 27 Jan. Action – Ian Poole to guide

- Decision made to arrange a meeting with Ian P to clarify further issues before we spend time going through document line by line for final edit. Action, HW to confirm attendance of IP at meeting on 24 Jan.

- Do we need a section on Local Business.  Information from local businesses could be obtained during the 6 week Consultation Period.

- Section on infrastructure needs developing as missing at present.

- Preparation for Consultation

To continue working towards consultation on Saturday 15 February. For further discussion with Ian P when we meet with him.

Action: HW to book the village hall for 15 February.

- Funding for next financial year.

Our funding will expire on 31 March and there is not sufficient time to receive all the likely charges that may be incurred.

- Action: AH to apply for new funding from 1 April. HW to raise with PC to see if funding pot is still available from PC.

- Propose idea of “Village Life” Events

It was suggested by HW and CH to arrange Village night events at the Shoulder of Mutton.  These nights could be once a quarter and advertised in the Assington News. They could be for residents to meet up and be a way for new residents to get to know people. They would also help support the pub. Action: AH and NF to confirm arrangements with the pub landlord.  Then inform CH and a release for Assington News prepared.

Meeting finished @ 21.00

Dates of next meetings:	Friday 24 January at Andrews House Time tbc

Monday 3 February in Village Hall